## Sheet1
SecureVote Faculty
Project Plan
| Task | Owner | Start | Duration (days) | End | Depends on | Completion(%)
| Project Kick-off | PM | 2026-05-26 |  | 2026-05-26
| Requirement review and branstorming | The whole team | 2026-05-26 | 3 | 2026-05-29 | Project kickoff | 100
| UI Wireframes | UI/UX Designer | 2026-05-29 | 5 | 2026-06-05 | Requirement review and branstorming | 50
| Database Schema and Backend architecture design | Backend Developer | 2026-05-29 | 5 | 2026-06-05 | Requirement review and branstorming | 30
| UI Wireframes/Backend Arch.. Validation and Approval (Apv1) | The whole team | 2026-05-31 | 2 | 2026-06-05 | Ui Wireframes & Db schema and Arch Design
| UI/UX Design | UI/UX Designer | 2026-06-05 | 16 | 2026-06-29 | (Apv1)
| Building of Frontend | Frontend Developer | 2026-06-12 | 12 | 2026-06-30 | UI/UX Design
| Backend/Api developent | Backend Developer | 2026-06-05 | 10 | 2026-06-19 | (Apv1)
| Private AWS Server setup (VPC, VC2, Congnito) | Backend Developer | 2026-06-19 | 7 | 2026-06-30 | Backend/Api developent
| Device Encryption System | Backend Developer | 2026-06-30 | 6 | 2026-07-08 | Private AWS Server setup (VPC, VC2, Congnito)
| Deployment of Backend to Aws | Backend Developer | 2026-07-08 | 3 | 2026-07-13 | Device Encryption System
| Integration of Backend to Frontend | Frontend Developer | 2026-07-13 | 6 | 2026-07-21 | Deployment of Backend to Aws
| Deployment of Frontend to Vercel & domain configuration | Frontend Developer | 2026-07-21 | 2 | 2026-07-23 | Integration of Backend to Frontend
| Testing | Tester | 2026-07-23 | 3 | 2026-07-28 | Deployment of Backend & Frontend App
| Launch | Project MGT | 2026-07-28 | 1 | 2026-07-29 | Testing
[6 empty] | Full Completion | 1.8
Milestone chart
| Phases | Target (days) | Status
1 | Design Validation (Schema & Wireframe) | 10 | Completed
2 | UI design and building | 25 | Inprogress
2 | Auth & Encryption setup | 33 | Pending
3 | Integration of System | 13
4 | Deployment & Testing | 20
5 | Launching | 1
Risk Resgister
# | Risk | Category | Likelihood | Impact | Risk Level | Mitigation
1 | Team member diverting from initial goal | People | High | High | Critical | Group brainstorming will be done before project kickoff
2 | Client changes scope after development starts | Scope | High | High | Critical | Sign off scope in writing before development
3 | Student data entry form has usability issues | Technical | Medium | Medium | Medium | Conduct usability testing with 3 real students
4 | Hosting server goes down at launch | Technical | Low | High | Medium | Use a cloud provider with 99.9% uptime SLA
5 | API for email notifications is deprecated | Technical | Low | Medium | Low | Choose a maintained provider; have a backup
Formulas:
End = [Start]
End = WORKDAY([Start],[Duration (days)])
Start = [End, row above]
Start = SUM([Start, row above],2)