## Slide 1
Week 7: Execution Tracking
Raji Victor Oluwapelumi
Corporate Strategy & Operations
07
Executive Briefing
Dashboards · Timeline Variance · Critical Path · Float · Bottlenecks

## Slide 2
Planning vs. Execution Tracking
Shifting from theoretical roadmaps to operational reality
Project Planning
Theoretical Roadmap
Defines the ideal sequence of events and
dependencies based on initial assumptions.
Baseline Success
Establishes the standard against which all future
progress will be measured.
Strategic Allocation
Focuses on high-level resource distribution and
long-term milestone setting.
Execution Tracking
Operational Reality
Captures day-to-day progress, surfacing the truth
of project momentum.
Variance Detection
Identifies deviations from the plan early enough to
enable proactive correction.
Data-Driven Agility
Provides the evidence required to make informed
adjustments to the original strategy.
SECTION 01 / PAGE 02

## Slide 3
THE OPERATIONAL LENS
The “Sprint” Board
“What am I working on today?"
To Do / In Progress / In Review / Done columns
Task-level detail
Updated continuously by the team
Used by: developers, Scrum Master, PO
THE EXECUTIVE LENS
The “Delivery” Dashboard
"Is this project going to deliver on time?"
Overall status: Green / Amber / Red
% complete, story points burned vs remaining
Active blockers & upcoming milestones
Used by: supervisors, clients, faculty HOD
SECTION 01 / PAGE 03
For the development team
For stakeholders & supervisors

## Slide 4
Timeline Management
STATUS COMMUNICATION STANDARDS
On Track
Proceeding as planned with no known risks to the critical path.
At Risk
Facing potential delays; mitigation strategies are currently in progress.
Off Track
Milestone missed or critical delay; immediate executive intervention required.
EXECUTIVE REPORTING EXAMPLE
Standard Reporting
"We are working on the database schema and it's taking a bit longer than we thought it would."
Premium Reporting
“SF-12 is 3 days behind due to [reason]. This affects SF-15. We are [action] to recover [X] days. New launch date: [date]”
SECTION 01 / PAGE 04

## Slide 5
The Critical Path
CORE DEFINITION
The longest sequence of dependent tasks through a project which must be completed on time for the project to finish on its due date.
Any delay in a critical path task directly impacts the final project completion date.
Managing the critical path is the primary objective of professional execution tracking.
Resources should be prioritized for these tasks to ensure zero variance from the baseline.
Path 1: A→B→D => 3 + 5 + 4 = 12 days = CRITICAL
Path 2: A→C→D => 3 + 2 + 4 = 9 days (shorter)
Case Study: SF-8
The Database Schema (SF-8) serves as the technical foundation for all subsequent development chains.
Current Status
In Progress with a 3-day variance against
the original baseline.
Strategic Impact
This delay causes an immediate 3-day
slip to the final integration milestone.
SECTION 02 / PAGE 05

## Slide 6
CORE CONCEPT
Understanding Float (Slack)
The amount of time a task can be delayed without affecting the project's overall end date.
The Executive Rule
Protect the critical path at all costs; use float as a strategic buffer for non-critical risks. Tasks with zero float are, by definition, on the Critical Path.
CALCULATION LOGIC
Strategic Buffer Analysis
Parallel Path (Task B)
5 Days
Current Task (Task C)
2 Days Active + 3 Days Float
Calculation Result:
5 Days - 2 Days = 3 Days Float
SECTION 02 / PAGE 06

## Slide 7
GOVERNING PATH ★ CRITICAL
Frontend Chain
SF-7 UI Wireframes
7 Days
SF-10 UI/UX Design
24 Days
SF-11 Build Frontend
18 Days
Total Duration
49 Days
PARALLEL PATH
Backend Chain
SF-8 Database Schema
7 Days
SF-12 Backend/API
14 Days
SF-15 Deploy Backend
5 Days
Total Duration
26 Days
STRATEGIC IMPLICATION
The Frontend Chain governs the launch date. Resources must be prioritized here to protect the timeline, as the Backend Chain currently maintains 23 days of float.
CASE STUDY / PAGE 07

## Slide 8
Bottleneck Detection
Identifying constraints in the delivery pipeline
TO DO
2
tasks
IN PROGRESS
3
tasks
IN REVIEW
9
tasks (bottleneck)
DONE
5
tasks
Visual Indicators
One stage has significantly more tasks than any other in the pipeline.
Work-in-Progress (WIP) continues to grow without corresponding completions.
Operational Signals
Tasks sit in a specific status much longer than the historical average.
One individual or resource has far more active tasks than the rest of the team.
SECTION 03 / PAGE 09

## Slide 9
Fixing the Bottleneck
Applying the Theory of Constraints to delivery
THE PROBLEM
Systemic Stall
Four critical tasks (SF-7 to SF-10) are stalled in the 'In Review' stage.
Single Product Owner creates a linear dependency for parallel work.
STRATEGIC ACTION
Capacity Expansion
Train a secondary reviewer to verify work against the Definition of Done.
Delegate approval authority for non-critical UI components.
THE IMPACT
Restored Velocity
Review cycle time reduced by 60%, clearing the backlog within 48 hours.
Overall chain velocity increases as downstream tasks are unblocked.
SECTION 03 / PAGE 10

## Slide 10
Live Execution Tracker
SecureVote Faculty — Week 7 Snapshot
TASK
OWNER
PLANNED END
ACTUAL/EST
STATUS
VARIANCE
CRITICAL?
SF-6
Requirements
VR
May 29
May 29
Done
0
No
SF-7
UI Wireframes
—
Jun 05
Jun 08
In Progress
+3 days
★ Yes
SF-8
Database Schema
—
Jun 05
Jun 05
To Do
0
★ Yes
SF-12
Backend/API
—
Jun 19
TBD
To Do
—
No (float)
SF-10
UI/UX Design
—
Jun 29
TBD
To Do
—
★ Yes
SF-11
Build Frontend
—
Jun 30
TBD
To Do
—
★ Yes
★ = On Critical Path (Zero Float) — Any delay in these tasks directly shifts the final launch date.
TRACKER / PAGE 11

## Slide 12
Weekly Status Update
ON TRACK
EXECUTIVE SUMMARY
Week 7 Performance
Core requirements and initial wireframes are 100% finalized. The database schema is ready to commence on schedule, maintaining alignment with the original project baseline.
PROGRESS METRICS
Completion & Velocity
2 of 19 total tasks (~10.5%) completed. Critical path focus remains strictly on Frontend development chains to protect the final launch date.
RISK ASSESSMENT
Mitigation & Blockers
No active blockers identified. SF-8 remains the immediate priority. Resource allocation is optimized for critical path tasks.
FORWARD PLANNING
Immediate Next Steps
Initiate SF-12 Backend/API development immediately upon SF-8 validation. Conduct mid-week review of Frontend chain progress.
EXECUTIVE SUMMARY / PAGE 12

## Slide 14
KEY TAKEAWAY
Planning tells you what should happen. Tracking tells you what is happening.
The critical path tells you what to protect. Float tells you what you can afford to lose. Bottlenecks tell you where to focus. Together, they are how you stay in control of your delivery.
EXECUTIVE SUMMARY / PAGE 13