## Slide 1
STRATEGIC PRIORITIZATION
Delivery Risk: The Critical Path Lens
Raji Victor Oluwapelumi
The Core Question
"Does this risk threaten a zero-float task?"
RISK VS. CRITICAL PATH
Fundamental Alignment
Delivery risk is fundamentally about what threatens your critical
path.
Lower Priority Risks
A risk that only affects a task with float is lower priority because
you have buffer to absorb it.
Higher Priority Risks
A risk that affects a critical path task is automatically higher
priority because there is no buffer.
SECTION 04 / PAGE 14

## Slide 2
Categories of Delivery Risk
Identifying systemic threats to project momentum
Technical Risk
The solution might not work as designed, such as an encryption library having compatibility issues.
Schedule Risk
A task takes longer than planned, for example, UI/UX Design running over its 24-day estimate.
Resource Risk
A person, tool, or budget becomes unavailable, such as the only backend developer falling ill.
External Risk
Factors outside your control, such as AWS account approval delays or unavailable faculty admin.
Scope Risk
Uncontrolled growth of requirements, remaining a critical factor from previous project phases.
SECTION 04 / PAGE 15

## Slide 3
SecureVote Risk Identification
Analyzing priority through the critical path lens
RISK
CATEGORY
ON CRITICAL PATH?
PRIORITY
UI/UX Design (SF-10) over 24-day estimate
Schedule
Yes (Zero Float)
Critical
Backend/API (SF-12) delayed by 2 weeks
Schedule
No (23 Days Float)
Low (Absorbable)
AWS account approval delay
External
No (Non-critical chain)
Medium
Designer (SF-10/11) becomes unavailable
Resource
Yes (Critical Path)
Critical
Device encryption library security flaw
Technical
No (Float available)
Medium
THE CRITICAL LENS
A 2-week delay is Critical for SF-10 but Low for SF-12, purely based on their position relative to the critical path. This provides the essential context missing from generic risk registers.
RISK ANALYSIS / PAGE 16

## Slide 4
OPERATIONAL FRAMEWORK
The Escalation Framework
The structured process of raising an issue to someone with more authority or resources when you cannot resolve it at your current level.
WHY ESCALATIONS FAIL
Timing Issues
Raising the issue too late to enable effective executive
intervention or resource reallocation.
Information Gaps
Escalating without the specific data or factual context required
for a senior decision.
THE CORE PRINCIPLE
The Golden Rule
"Escalate based on impact and time-sensitivity, not based on how uncomfortable the conversation feels."
ESCALATION / PAGE 17

## Slide 5
The Escalation Ladder
LEVEL 01
Self-Resolve
The individual doing the work attempts to solve the issue independently within a reasonable timeframe, typically same-day.
LEVEL 02
Team-Resolve
If self-resolution fails, the issue is raised to the team during standup for collective troubleshooting and peer support.
LEVEL 03
Scrum Master / PM-Resolve
If the team cannot resolve the blocker, the PM intervenes to remove organizational obstacles or secure necessary resources.
LEVEL 04
Stakeholder / Sponsor
If the issue threatens project timeline, budget, or scope beyond PM authority, it is escalated to senior stakeholders for strategic approval.
ESCALATION / PAGE 18

## Slide 6
The Anatomy of a Good Escalation
Ensuring clarity and action-oriented communication
OBJECTIVE DEFINITION
What is the issue?
Provide a factual and objective description of the blocker, avoiding emotional framing or subjective assessments.
DUE DILIGENCE
What have you tried?
Demonstrate that Level 1 (self-resolve) and Level 2 (team-resolve) attempts have occurred prior to escalating.
STRATEGIC CONTEXT
What is the impact?
Directly tie the unresolved risk to the critical path, project deadline, or overall budget constraints.
SPECIFIC REQUEST
What do you need?
Be specific about the required decision, resource, or authority rather than making a general request for assistance.
ESCALATION / PAGE 19

## Slide 7
Recovery Planning Techniques
Crashing
Adding more resources to a specific task to shorten its overall duration, typically involving additional financial expenditure.
TRADEOFF: INCREASED COST AND COORDINATION OVERHEAD.
Fast-tracking
Executing tasks in parallel that were originally planned to occur sequentially, requiring work to overlap across stages.
TRADEOFF: HIGHER RISK OF REWORK DUE TO OVERLAPPING DEPENDENCIES.
Re-scoping
Reducing the breadth of what will be delivered to recover lost time, utilizing the MoSCoW prioritization model.
TRADEOFF: REDUCTION IN TOTAL DELIVERED FUNCTIONALITY.
RECOVERY / PAGE 20

## Slide 8
Choosing a Recovery Technique
Strategic tradeoffs in project stabilization
TECHNIQUE
BEST WHEN
COST
RISK
Crashing
Budget is available and the task is parallelizable.
High (Extra Cost)
Medium (Coordination)
Fast-tracking
Some overlap is tolerable and the deadline is fixed.
Low
High (Rework Risk)
Re-scoping
Both deadline and budget are fixed.
None
Low (if MoSCoW used)
RECOVERY / PAGE 21

## Slide 9
Recovery Decision Flow
STEP 01
Critical Path Assessment
Is the delay on the critical path? If no, do nothing; the available float will absorb the variance without impacting the final deadline.
STEP 02
Resource Capacity Check
If yes, can you add resources without breaking the budget? Consider crashing to shorten the task duration through extra expenditure.
STEP 03
Structural Overlap Check
If the budget is fixed, can some tasks overlap safely? Consider fast-tracking to execute sequential tasks in parallel.
STEP 04
Strategic Re-scoping
If neither works, re-scope the project. Cut "Could Have" or "Won't Have" features using your established MoSCoW backlog.
RECOVERY / PAGE 22